## DASHBOARD
Dashboard
HOMIZI: start from an empty project, install an early Android build, iterate with tester distribution, then release on Google Play. Keep iOS-compatible Flutter architecture.
Topic | Recommendation | Details
Recommended path | Android first | Get a real app onto your phone early; continue towards Play Store while preserving iOS support.
Mobile framework | Flutter + Dart | One shared codebase; native iOS release still requires macOS/Xcode or macOS CI.
Backend default | Supabase + PostgreSQL | Proposed, not approved. Confirm provider, region, cost, privacy and access rules before production.
First install | USB + flutter run | Fastest for a first device smoke test; no store account required.
Repeatable installs | Firebase App Distribution | Invite yourself/testers and share each new test build. New Flutter code normally requires a new build/install.
Live backend changes | Deploy backend separately | Content/data and compatible server logic can update without reinstalling the app.
Play Store release | Signed AAB + Play Console | Store review and account-specific testing requirements still apply.
Important current policy | Target API 36+ | Google's official policy page states new apps/updates must target Android 16/API 36+ from Aug 31, 2026; recheck at release.
Applicable new personal accounts | 12 testers / 14 days | Google says personal developer accounts created after Nov 13, 2023 need a closed test with at least 12 opted-in testers continuously for 14 days before applying for production access.
How to use this workbook | One task at a time | Update status only after evidence. Stop at gates requiring owner, security, finance or legal approval.
Pipeline completion
Total steps | 38
Done | 0
Blocked | 0
Review required | 0
Official references
Flutter Android deployment | https://docs.flutter.dev/deployment/android
Firebase App Distribution | https://firebase.google.com/docs/app-distribution/android/distribute-console
Play testing requirements | https://support.google.com/googleplay/android-developer/answer/14151465?hl=en
Play target API level | https://support.google.com/googleplay/android-developer/answer/11926878?hl=en-EN
Flutter install | https://docs.flutter.dev/get-started/install

## EXECUTION_PIPELINE
Execution Pipeline
Sequential execution checklist. Dependencies use step IDs. Cursor writes code; you approve provider, privacy, financial, destructive and production decisions.
Step ID | Phase | Work package | Detailed actions | Definition of done / evidence | Owner | Dependencies | Status | Approval type | Notes
E-001 | P0 Scope | Approve MVP | Review features and select minimum releasable slice: profiles, listing creation, discovery, safety/reporting. Defer payments and real ID verification unless essential. | Approved product brief and deferred-scope list in docs/PRODUCT_SPEC.md. | Owner | Start | Not started | Owner approval | No existing project assumed.
E-002 | P1 Setup | Install tools | Install Flutter/Dart, Android Studio+SDK, Git, Cursor. Run flutter doctor and git --version. | Toolchain report saved; fix blocking Android toolchain issues. | Owner | E-001 | Not started | Owner action | Windows can build Android; iOS needs macOS/Xcode.
E-003 | P1 Setup | Create repo | Create GitHub repo and local homizi folder; initialize README and .gitignore. | Initial commit; no credentials committed. | Owner + Cursor | E-002 | Not started | Routine | Choose stable package/bundle ID early.
E-004 | P1 Setup | Create Flutter app | Create Flutter project targeting Android+iOS and run on emulator. | Starter app launches; iOS project files exist. | Cursor | E-003 | Not started | Routine | Do not implement all features at once.
E-005 | P1 Setup | Architecture & quality | Add feature-first folders, navigation, one state-management approach, linting and first widget test. | dart format, flutter analyze and flutter test pass. | Cursor | E-004 | Not started | Routine | Avoid unnecessary dependencies.
E-006 | P1 Device | First phone install | Enable Android Developer options + USB debugging; run flutter devices and flutter run -d DEVICE_ID. | Starter app runs on physical phone; record OS and screenshot. | Owner + Cursor | E-004 | Not started | Routine | First install happens before backend/store.
E-007 | P2 Decision | Approve backend | Evaluate Supabase/Firebase/custom backend, region, cost, terms and features. | Decision recorded in DECISIONS.md with owner/date. | Owner | E-001 | Not started | Security review | Supabase is a proposal only.
E-008 | P2 Backend | Create dev environment | Create development backend; configure auth/storage/database and environment variables; document .env.example. | Dev project reachable; secrets excluded from Git. | Owner + Cursor | E-007 | Not started | Owner + review | No production data yet.
E-009 | P2 Backend | Schema migrations | Create minimal tables for users/profiles, preferences, listings/photos, interests/matches, reports/blocks and consent. | Migrations run from clean state; schema and seed data documented. | Cursor | E-008 | Not started | Review | Build only what MVP needs.
E-010 | P2 Security | Authorization policies | Add server-side/RLS rules and negative tests for cross-user access, ownership, contact privacy and admin access. | Allowed and denied cases tested; no client-only security gates. | Cursor + reviewer | E-009 | Not started | Security gate | Required before real users.
E-011 | P3 Design | Design system | Build HOMIZI tokens, buttons, form fields, listing cards, photo grid and loading/error/empty states. | Reusable accessible components used across screens. | Cursor + owner | E-004 | Not started | Owner review | Use approved logo/colors.
E-012 | P4 Auth | Authentication | Implement selected provider's login/OTP, sessions, logout, expiry and error states. | Auth works in development; invalid/expired attempts tested. | Cursor | E-008,E-011 | Not started | Review | Never log OTP/tokens.
E-013 | P4 Profiles | Tenant and host profiles | Implement role selection, profile fields and consent capture; use test verification status only. | Validated role flows and access rules pass. | Cursor | E-010,E-012 | Not started | Review | No real Aadhaar/face data without approval.
E-014 | P5 Requirements | Tenant requirement flow | Budget, locality, move-in date, occupancy, property type, furnishing and preferences. | Create/edit/draft validation works with tests. | Cursor | E-013 | Not started | Routine | Collect minimum necessary data.
E-015 | P5 Listings | Host listing form | Property details, rent/deposit/charges, amenities, restrictions, draft and preview. | Host can create/edit/preview valid draft. | Cursor | E-013 | Not started | Routine | Precise address visibility needs decision.
E-016 | P5 Photos | Upload and order photos | Minimum count, order rules, primary image, retry/progress, remove/reorder and server validation. | Invalid file, ownership, ordering and retry tests pass. | Cursor | E-008,E-015 | Not started | Security review | Storage access must be restricted.
E-017 | P5 Publish | Publish validation | Validate required fields/photos and moderation state on server before publish. | Invalid listing cannot publish through UI or API. | Cursor | E-010,E-016 | Not started | Security review | Server is authoritative.
E-018 | P6 Discovery | Feed and filters | Build feed, detail, filters, sorting, pagination and empty/loading/error states. | Works on phone; private fields excluded from results. | Cursor | E-017 | Not started | Routine | Start with seed data.
E-019 | P6 Matching | Compatibility score | Approve factors/weights and implement server-side explainable scoring. | Documented formula and deterministic tests. | Cursor + owner | E-018 | Not started | Owner review | Avoid discriminatory criteria.
E-020 | P6 Matching | Interest and mutual match | Like/pass/save and reciprocal matching with idempotency, block checks and rate limits. | Duplicate requests do not create duplicate matches. | Cursor | E-010,E-019 | Not started | Security review | Server authoritative.
E-021 | P6 Privacy | Contact gate | Approve disclosure rules; return contact only via authorized server operation after required match/consent. | Unauthorized tests prove contact fields absent from payloads. | Owner + Cursor | E-020 | Not started | Explicit approval | Stop until policy is approved.
E-022 | P7 Safety | Report and block | Report users/listings, block actions, moderation state and audit trail. | Blocked interactions fail; reports reach a defined moderation workflow. | Cursor + owner | E-010,E-018 | Not started | Human review | Assign moderation responsibility.
E-023 | P7 Optional | Chat, visits, notifications | Decide MVP inclusion and providers; implement match-gated chat, visit state machine and push/in-app alerts if approved. | Each chosen flow has auth checks and failure-state tests. | Owner + Cursor | E-020,E-021 | Not started | Approval | Defer to ship sooner if acceptable.
E-024 | P8 Optional | Payment go/no-go | Review plans, gateway, store policy, refunds/tax/accounting and webhooks. | Written decision; no fake checkout if deferred. | Owner + finance | E-001 | Not started | Approval gate | Recommended to defer if not essential.
E-025 | P9 QA | Automated test suite | Unit/widget/integration, backend policy, upload and main journey tests; run formatter/analyzer/tests. | CI green with evidence and no unreported failures. | Cursor | E-012:E-023 | Not started | Review | Actual tests must run.
E-026 | P9 QA | Physical device regression | Test network changes, offline/slow mode, resume, app update and core journeys on Android phone. | No release-blocking defects; repro steps logged. | Owner + Cursor | E-025 | Not started | Human testing | Real device needed.
E-027 | P9 Security | Security/privacy audit | Review data inventory, policies, secrets, upload validation, deletion, logging, dependency checks and threat model. | No unresolved critical/high issues; evidence recorded. | Reviewer | E-010,E-021,E-022,E-025 | Not started | Required gate | Mocks until provider approved.
E-028 | P10 Test delivery | Firebase App Distribution | Create Firebase project/app with exact package name; invite testers; upload APK and share release link. | Tester can install a release and see version/release notes. | Owner + Cursor | E-004,E-026 | Not started | Owner action | Good repeatable pre-store testing route.
E-029 | P10 Automation | Automate test builds | CI runs checks, builds APK on approved branch/tag and uploads to Firebase only when secrets/config are present. | Traceable build releases; failed jobs report errors safely. | Cursor + owner | E-025,E-028 | Not started | Review | Protect secrets/branches.
E-030 | P10 Play Store | Create Play Console app | Create developer account/app record; set package name, listing draft, access and policy forms. | Console setup checklist complete. | Owner | E-004 | Not started | Owner action | Account verification/fees may apply.
E-031 | P10 Play Store | Signed AAB | Configure upload signing securely, version/build number and target API; build release AAB and verify artifact. | Signed AAB exists; signing secrets not committed. | Cursor + owner | E-027,E-030 | Not started | Review | Flutter recommends AAB for Play.
E-032 | P10 Compliance | Store listing and declarations | Icon, screenshots, description, content rating, privacy policy, data safety, permissions, account deletion and support URLs. | Declarations match actual SDK/data behavior. | Owner + reviewer | E-027,E-030 | Not started | Legal/owner review | No placeholder or false claims.
E-033 | P10 Testing | Play internal testing | Upload AAB to internal testing; add testers; install from Play opt-in link and test upgrade path. | Internal track installation verified; issues fixed. | Owner + Cursor | E-031,E-032 | Not started | Human testing | Different from Firebase distribution.
E-034 | P10 Testing | Closed test and production access | For applicable new personal accounts, maintain at least 12 opted-in testers continuously for 14 days, then apply for production access. | Test evidence and production-access application recorded. | Owner | E-033 | Not started | External wait | Verify account-specific current rules.
E-035 | P10 Release | Release readiness gate | Review test evidence, policies, crash status, support, moderation, backup, rollback and owner approval. | Written go/no-go; no critical/high issue unresolved. | Owner + reviewers | E-027,E-032,E-034 | Not started | Human approval | No unattended publishing.
E-036 | P10 Release | Submit to production | Submit signed AAB; answer review questions; resolve feedback; staged rollout if available. | Play Console reports approved/released and public URL is recorded. | Owner | E-035 | Not started | Human action | Review timing is not guaranteed.
E-037 | P11 Ops | Monitor and improve | Monitor crashes, auth, listings, reports, support and costs; define hotfix/rollback process. | Alerts and operational owner assigned; review cadence active. | Owner + Cursor | E-036 | Not started | Ongoing | Launch begins operations.
E-038 | P11 iOS | Prepare iOS release | Use Mac/Xcode or macOS CI; configure signing, iOS tests, TestFlight and App Store metadata. | iOS release candidate passes checks and is ready for separate review. | Owner + Cursor | E-025,E-027 | Not started | Separate approval | Do not block Android MVP.

## CURSOR_PROMPTS
Cursor Prompts
Copy one task prompt at a time into Cursor Agent. Never ask the agent to build everything in one shot.
Prompt ID | Purpose | Prompt to paste into Cursor | Use when
CP-001 | Create specs | This is a brand-new HOMIZI project with no code. Read this workbook's dashboard, execution pipeline, decisions, modules, screens, data model, security, tests and store release sheets. Create docs/PRODUCT_SPEC.md, TECH_STACK.md, DATA_MODEL.md, SECURITY_AND_PRIVACY.md, RELEASE_PLAN.md and DECISIONS.md. Preserve requirements; mark undecided choices as pending. Do not build app yet. Report open questions and wait for my approval. | Q-001 scope/specification
CP-002 | Environment baseline | Check flutter --version, flutter doctor, git --version and flutter devices. Report exact output and blockers. Do not claim iOS builds work on Windows. Do not install system tools or change global settings without explaining first. | Q-002 setup
CP-003 | Flutter baseline | Create a Flutter app targeting Android and iOS with the approved package ID, a simple HOMIZI home screen, feature-first structure, linting and one widget test. Run dart format, flutter analyze, flutter test and Android debug build. Fix failures; report exact commands and results. | E-004/E-005
CP-004 | Backend security | Implement only approved development schema/policies. Add negative tests for cross-user access and private contact fields. Keep migrations versioned. Never place privileged keys in the app. Stop if backend provider or region is unapproved. | E-009/E-010
CP-005 | One task template | Implement only [STEP ID + WORK PACKAGE] from EXECUTION_PIPELINE. Before coding, summarize dependencies and acceptance criteria. Make real repository changes, run formatting/analyzer/tests/build as relevant, fix failures, update docs and report changed files, actual commands/results, blockers and next task. Mark Done only if criteria pass. | Use for each approved step
CP-006 | Phone APK | Verify package ID and current build. Run tests, then build debug APK using flutter build apk --debug. Give exact artifact path and steps to install on my Android phone. If Firebase App Distribution is configured, upload only if authorized and provide actual release link; otherwise give manual setup steps. Do not claim distribution succeeded without proof. | E-006/E-028
CP-007 | CI distribution | Set up GitHub Actions to run format/analyze/tests on pull requests and build/distribute a test APK only from an approved branch/tag. Use repository secrets; fail safely if missing; never print secrets. Do not deploy production from arbitrary commits. | E-029
CP-008 | Release audit | Audit every TEST_PLAN, SECURITY_PRIVACY and STORE_RELEASE item as Pass/Fail/Not tested with evidence. Run available checks. Do not infer pass from missing evidence. List blockers and fixes. Do not submit/publish without explicit owner approval. | E-035

## PHONE_LIVE_UPDATES
Phone Live Updates
Three different update types: local development, app binary updates, and backend/content updates. Configure each deliberately.
ID | Goal | Steps | Success condition | Channel
L-01 | Immediate local install | Enable Developer options and USB debugging on Android. Connect USB; accept trust prompt. In Cursor terminal run flutter devices, then flutter run -d <deviceId>. | HOMIZI starter app launches on the physical phone with logs available. | Local debug
L-02 | APK without USB | Run flutter build apk --debug. Transfer build/app/outputs/flutter-apk/app-debug.apk to phone; open it and allow installation from that source if prompted. | APK installs. For subsequent upgrades, keep same application ID and signing key. | Manual APK
L-03 | Repeatable tester install | Create Firebase project and register Android app using exact package name. Invite your tester email. Upload APK in Firebase App Distribution console or via CLI; share the release link/invitation. | Phone can install releases and see notes/version; test releases are available for limited time per Firebase rules. | Firebase App Distribution
L-04 | Automatic build distribution | Configure GitHub Actions: run tests → build APK → upload to Firebase only on approved branch/tag → publish release notes/link. Store tokens in repository secrets. | Each approved commit/tag yields a traceable test build; failures notify rather than silently publish. | GitHub Actions + Firebase
L-05 | Live data/backend | Deploy approved backend migrations/functions and have the app fetch data from the backend. Use compatible API/schema changes and a rollback plan. | Content/server-side updates appear without reinstall when installed client supports them. | Backend deployment
L-06 | UI/code changes | For Flutter UI/native code changes, create a new build and install via Firebase or Play testing. Do not assume silent hot updates. Evaluate any OTA product only after policy/security review. | New app code is installed as a new build. | New binary
L-07 | Play internal testing | Upload signed AAB in Play Console internal testing, add testers and share opt-in link. Test install/update through Google Play. | Validates Play signing and Play update flow. | Play Console
L-08 | Production | After all gates, submit signed AAB, complete declarations, answer review questions and release with staged rollout if available. | Public Play listing is approved and live. | Google Play
L-09 | iOS testing | Build on macOS/Xcode or macOS CI, configure signing and distribute through TestFlight. Each build is uploaded and tested under Apple's process. | iPhone tester installs via TestFlight. | TestFlight

## DECISIONS
Decisions
Fill and approve these before the related implementation. Proposed values are not final approval.
ID | Decision | Recommended default | Alternative / note | Status | Approver
D-01 | Framework | Flutter + Dart for one shared iOS/Android codebase. | React Native if team chooses TypeScript stack. | Proposed | Owner
D-02 | Backend | Supabase/PostgreSQL proposed for relational listings, auth, storage and row-level security. | Firebase/custom backend after review. | Proposed | Owner + security
D-03 | Launch scope | Android-first installable MVP; maintain iOS compatibility; defer optional features. | Ship broader scope only if owner approves timeline. | Proposed | Owner
D-04 | Verification | Mock verification status in dev; select compliant provider only after privacy/legal review. | Provider decision must include retention and data-flow. | Not selected | Legal/security
D-05 | Contact privacy | Contact returned only through server authorization after explicit approved conditions. | Owner must define exact mutual-match/consent rules. | Not selected | Owner + security
D-06 | Payments | Defer real payments until policy, finance and gateway review. | Include only if essential to MVP. | Not selected | Owner + finance
D-07 | Package ID | Choose permanent reverse-domain Android applicationId and iOS bundle identifier. | Do not casually change after release. | Pending | Owner
D-08 | Production region | Choose backend region after latency, privacy and contractual review. | Do not assume provider default is suitable. | Pending | Owner + privacy
D-09 | Store account type | Confirm Apple/Google account owner and whether Play account is personal or organization. | Account type affects verification/testing steps. | Pending | Owner
D-10 | Moderation | Assign who reviews reports and expected response process before public launch. | Do not launch open marketplace without operations plan. | Pending | Owner

## PLAYSTORE_CHECKLIST
Playstore Checklist
Store release checklist; verify current official rules when preparing submission.
ID | Checklist | Acceptance criteria | Owner | Status | Notes
R-01 | Account setup | Create/verify Google Play Console account and app record. | Owner | Not started | Account type may trigger closed testing requirement.
R-02 | Package and signing | Choose stable package name; configure upload key/app signing securely; do not commit keys. | Owner + Cursor | Not started | Backup signing material securely.
R-03 | Target SDK | Check current Play target API policy; as of official policy page checked Oct 2026, new apps/updates target API 36+ from Aug 31 2026, subject to exceptions/extensions. | Cursor + owner | Not started | Recheck official page at release.
R-04 | Release artifact | Run tests and build signed release AAB using flutter build appbundle. | Cursor | Not started | Flutter docs say Play prefers app bundle.
R-05 | Store listing | Icon, screenshots, description, category, contact/support details. | Owner + Cursor | Not started | Must reflect actual app.
R-06 | Privacy and safety | Publish privacy policy, terms, support/safety page, account deletion flow and accurate data declarations. | Owner + reviewer | Not started | Declarations match actual SDK/data behavior.
R-07 | Testing track | Internal testing, then closed testing if applicable; capture tester feedback and fix issues. | Owner + testers | Not started | New personal accounts after 13 Nov 2023: at least 12 opted-in testers continuously for 14 days before production access application.
R-08 | Final QA | Physical-device tests, crash/permission checks, backend authorization and no critical/high defects. | Cursor + reviewer | Not started | Keep evidence.
R-09 | Go/no-go | Owner explicitly approves exact artifact, version, declarations and rollout. | Owner | Not started | Never auto-publish.
R-10 | Submit/release | Submit in Play Console; answer review questions; monitor review and staged rollout. | Owner | Not started | Approval is controlled by Google.
R-11 | Operations | Monitor crashes, reports, support, costs, auth and backend health; define rollback/hotfix process. | Owner + Cursor | Not started | App launch requires ongoing support.

## SECURITY_GATES
Security Gates
Do not release until critical security/privacy checks have evidence.
ID | Gate | Acceptance criteria | Status | Evidence
S-01 | Secrets | No API secrets, service-role keys, tokens or signing keys committed or embedded in mobile app. | Not started | Secret scan + repo review
S-02 | Authorization | Test cross-user read/write denial for profiles, listings, matches, chats and admin operations. | Not started | Negative access test report
S-03 | Contact privacy | Hidden contact fields never returned from unauthorized APIs; UI hiding alone is insufficient. | Not started | API response tests
S-04 | Identity data | No real Aadhaar/face data until provider, lawful basis, consent and retention are approved. | Not started | Approved provider/data-flow review
S-05 | Uploads | File size/type/ownership/access validation and listing photo moderation. | Not started | Upload tests
S-06 | Account deletion | Real deletion workflow across auth, database, storage and connected services according to approved policy. | Not started | End-to-end deletion evidence
S-07 | Moderation | Reports/blocks function and a named person/process handles reports. | Not started | Moderation SOP and integration test
S-08 | Payments | Server-verified webhooks and idempotency; no client-authoritative paid entitlements. | Not started | Webhook tests
S-09 | Backups | Production backup and restore procedure tested before launch. | Not started | Restore evidence
S-10 | Store declarations | Privacy/data safety declarations match SDKs, actual collection, sharing and retention. | Not started | Reviewed store forms
S-11 | Release rollback | Document how to halt rollout, disable feature and issue hotfix. | Not started | Runbook

## OFFICIAL_REFERENCES
Official References
Official documentation used for the pipeline. Re-check before launch because policy and pricing can change.
Reference | Official URL | Why it matters
Flutter install | https://docs.flutter.dev/get-started/install | Install SDK/toolchains.
Flutter Android release | https://docs.flutter.dev/deployment/android | Flutter APK/AAB build instructions; Google Play prefers AAB.
Firebase App Distribution | https://firebase.google.com/docs/app-distribution/android/distribute-console | Upload and distribute APK/AAB to testers.
Firebase tester setup | https://firebase.google.com/docs/app-distribution/get-set-up-as-a-tester | Accept invite and install tester build.
Play personal account testing | https://support.google.com/googleplay/android-developer/answer/14151465?hl=en | Applicable new personal accounts: closed test, 12 opted-in testers continuously for 14 days before production access request.
Play target API level | https://support.google.com/googleplay/android-developer/answer/11926878?hl=en-EN | Official current target API requirements; checked Oct 2026 page states API 36+ for new apps/updates from Aug 31 2026, subject to policy exceptions.
Google Play Console | https://play.google.com/console/ | App setup, testing tracks, submission.
Apple Developer | https://developer.apple.com/programs/ | Apple Developer Program.
App Store Connect | https://appstoreconnect.apple.com/ | iOS builds, TestFlight and App Store.
Supabase docs | https://supabase.com/docs | Auth, Postgres, storage, RLS, functions.
GitHub Actions | https://docs.github.com/actions | Automated CI and build workflows.

## HOW_TO_USE
How To Use
Use this workbook as a living task system with Cursor Agent.
Rule | Action | Reminder
1. Start | Read DASHBOARD, then approve D-01 through D-10 in DECISIONS. Start E-001 in EXECUTION_PIPELINE. | Do not begin with all features.
2. Task prompt | Copy the relevant prompt from CURSOR_PROMPTS and replace placeholders with exact step ID/work package. | One task per Cursor session is easiest to review.
3. Evidence | Save command outputs, screenshots, test results, build artifact links and decisions in GitHub/docs or the relevant tracker. | Do not mark Done without evidence.
4. Phone now | Complete E-002 through E-006 for a first local Android install; no backend needed for the first shell. | This is the earliest phone milestone.
5. Continuous testing | Complete E-028/029 to distribute new test builds via Firebase; keep version/build numbers increasing and signing consistent. | Each code/UI change usually requires reinstalling a new build.
6. Live updates | Deploy backend/content changes independently when backward-compatible; document migrations and rollback. | Not the same as hot-reloading app code.
7. Store | Follow PLAYSTORE_CHECKLIST; the store review and any required closed-test period cannot be automated away. | Google controls approval.
8. iOS | Maintain iOS target from day one but schedule signing/TestFlight/App Store steps on macOS/Xcode. | Android can be first without abandoning iOS.